## Sheet1
[6 empty] | Team Members | [9 empty] | Instructions: Fill in only green portions. For the activities table put number 1 in the square under each name if that individual participated in that activity. The number of hours for each individual will be calculated automatically. Readjust cell size to be sure all text is visible as needed.
[6 empty] | First Name | Last Name | Nickname (max 6 characters)
[6 empty] | Irfan | Ahmed | A.I
[6 empty] | Alec | Kurkdjian | Alec
[6 empty] | Cong-Vinh | Vu | CV
[6 empty] | Shadi | Makdissi | Shadi
[6 empty] | Ogo Oluwa | Jesutomi olasubulumi | Tomi
Add more rows as necessary
Activities Table
Date | Who |  |  |  |  | Type of Activty | Number of hourse spent | Purpose | Output | Hours spent
| A.I | Alec | CV | Shadi | Tomi |  |  |  |  | A.I | Alec | CV | Shadi | Tomi
Milestone 1
2019-09-05 | 1 | 1 | 1 | 1 | 1 | Meeting | 1 | Discuss about how we will manage our code and where it will be available for all member of the teams | We decided to use GitHub to store our documentation and code for the project | 1 | 1 | 1 | 1 | 1
2019-09-09 | 1 | 1 | 1 | 0 | 1 | meeting | 2 | Brainstorm ideas and come up with 6 opportunity statement | Came up with 6 ideas and opportunity statements | 2 | 2 | 2 | 0 | 2
2019-09-14 | 1 | 0 | 1 | 1 | 1 | Voice Call meetin | 2 | Create a WOT analysis of our 6 opportunity statement | Finished ranking our opportunity statement through a WOT analysis | 2 | 0 | 2 | 2 | 2
2019-09-19 | 1 | 1 | 1 | 1 | 1 | Meeting | 1 | Set Mission Statement | Finished writing down our mission statement for the chosen opportunity statement | 1 | 1 | 1 | 1 | 1
2019-09-21 | 1 | 1 | 1 | 1 | 1 | Voice Call meeting | 1 | Finalise report for Milestone 1 | We finished setting up our milestone 1 report in a word document | 1 | 1 | 1 | 1 | 1
[9 empty] | Total hours | 7 | 5 | 7 | 5 | 7
[9 empty] | Total team hours | [5 empty] | 31
Milestone 2
2019-10-01 | 1 | 1 | 1 | 1 | 1 | Voice Call meeting | 1 | Divide Milestone 2 task | Everyone has been assigned a specefic task related to milestone 2 | 1 | 1 | 1 | 1 | 1
2019-10-04 | 1 | 1 | 1 | 1 | 1 | Face to face meeting with stakeholder 1 | 1 | Interview with stakeholder 1 | Gathered information on stakeholder 1 and his point of view on our product | 1 | 1 | 1 | 1 | 1
2019-10-05 | 1 | 1 | 1 | 1 | 1 | Face to face meeting with stakeholder 2 | 1 | Interview with stakeholder 2 | Gathered information on stakeholder 1 and his point of view on our product | 1 | 1 | 1 | 1 | 1
2019-10-07 | 1 | 1 | 1 | 1 | 1 | Meeting | 1 | Finalise report for Milestone 2 | We finished setting up our milestone 2 report in a word document | 1 | 1 | 1 | 1 | 1
[9 empty] | Total hours | 4 | 4 | 4 | 4 | 4
[9 empty] | Total team hours | [5 empty] | 20
Sprint 1
2019-10-11 | 1 | 1 | 1 | 1 | 1 | Voice call meating | 2 | Prepare sprint 1 backlog and goals | We finished setting up our sprint 1 backlog and sprint 1 backlog | 2 | 2 | 2 | 2 | 2
2019-10-16 | 1 | 1 | 1 | 1 | 1 | Voice call meating | 1 | To get up to date of the team progress and the task they are working on | We got up to date on which task is being done by which teamates | 1 | 1 | 1 | 1 | 1
2019-10-18 | 1 | 1 | 1 | 1 | 1 | Voice call meating | 1 | To get up to date of the team progress and the task they are working on | We got up to date on which task is being done by which teamates | 1 | 1 | 1 | 1 | 1
2019-10-21 | 1 | 1 | 1 | 1 | 1 | Meeting in EV | 2 | Test out the log in/sign up page, home page and display history of the app. | The functionality are working and have found some points to improve | 2 | 2 | 2 | 2 | 2
2019-10-24 | 1 | 1 | 1 | 1 | 1 | Voice call meating | 2 | To get up to date of the team progress and the task they are working on | We got up to date on which task is being done by which teamates | 2 | 2 | 2 | 2 | 2
2019-10-25 | 1 | 0 | 0 | 1 | 1 | Meating in the lab room | 3 | Test the connection of the sensors with arduino | We were able to take picture and unlock the door with a motion sensor | 3 | 0 | 0 | 3 | 3
2019-10-26 | 1 | 1 | 1 | 1 | 1 | Voice call meating | 4 | Start and verify the sprint 1 document | We finished setting up our milestone 2 report in a word document | 4 | 4 | 4 | 0 | 4
2019-10-29 | 1 | 1 | 1 | 1 | 1 | Voice call meating | 2 | Sprint 2 backlog, goals and deciding what to demo | We finished setting up our sprint 2 backlog, goals and decided what to demo | 2 | 2 | 2 | 2 | 2
[9 empty] | Total hours | 17 | 14 | 14 | 13 | 17
[9 empty] | Total team hours | [5 empty] | 75
Sprint 2
2019-10-30 | 1 | 1 | 1 | 1 | 1 | Voice call meating | 1 | To get up to date of the team progress and the task they are working on and divide task for the sprint 2 document | We got up to date on which task is being done by which teamates and divided the documantion with each other | 1 | 1 | 1 | 1 | 1
2019-11-01 | 1 | 1 | 1 | 1 |  | Voice call meating | 1 | To get up to date of the team progress and the task they are working on | We got up to date on which task is being done by which teamates | 1 | 1 | 1 | 1 | 1
2019-11-04 | 1 | 1 | 1 | 1 | 1 | Meating in Ev | 3 | Testing the edit profile, adminastrator page, display history. | The functionality are working and have found some points to improve | 3 | 3 | 3 | 3 | 3
2019-11-05 | 1 | 1 | 1 | 1 | 1 | Meating in library | 2 | Testing if we can display the picture taken by the raspberryPi on the display history | We were sucessfully able to take and send a picture from raspberryPi to the app | 2 | 2 | 2 | 2 | 2
2019-11-06 | 1 | 1 | 1 | 1 | 1 | Voice call meating | 1 | To get up to date of the team progress and the task they are working on | We got up to date on which task is being done by which teamates | 1 | 1 | 1 | 1 | 1
2019-11-07 | 1 | 1 | 1 | 1 | 1 | Meating in library | 2 | Testing if the peak door and unlock door is working | We were sucessfully able to peak door and unlock the door lock | 2 | 2 | 2 | 2 | 2
2019-11-08 | 1 | 1 | 1 | 1 | 1 | Voice call meating | 2 | Sprint 2 grooming | We updated our product backlog | 2 | 2 | 2 | 2 | 2
2019-11-09 | 1 | 1 | 1 | 1 | 1 | Voice call meating | 2 | Finalize and verify the sprint 1 document | We finished setting up our milestone 2 report in a word document | 2 | 2 | 2 | 2 | 2
2019-11-10 | 1 | 1 | 1 | 1 | 1 | Voice call meating | 2 | Sprint 3 backlog, goals and deciding what to demo | We finished setting up our sprint 3 backlog, goals and decided what to demo | 2 | 2 | 2 | 2 | 2
[9 empty] | Total hours | 16 | 16 | 16 | 16 | 16
[9 empty] | Total Team hours | [5 empty] | 80
Sprint 3
[10 empty] | 0 | 0 | 0 | 0 | 0
[9 empty] | Total hours | 0 | 0 | 0 | 0 | 0
[9 empty] | total team hours | [5 empty] | 0
[9 empty] | Total hour over project | 44 | 39 | 41 | 38 | 44
[9 empty] | Total team hours over project | [5 empty] | 206