## Cover Page
Open Sesame
Prepared By:
Team D
Shadi Makdissi: 40060588
Cong-Vinh Vu: 40061685
Alec Kurkdjiani: 40056402
Irfan Ahmed: 40056645
Ogo-Oluwa Jesutomi Olasubulumi: 40055693

## Product Backlog
Product Backlog
Product Backlog
Story ID | Story Title | Card | Story Points/Size | Sprint | Status | Conversation | Confirmation
FE-1 | Main Page Buttons | As a presenter, I would like to be able to understand the functionality of each button so that I use the app without any difficulty (Story) | 1 | Sprint 1 | Completed | There will be 5 buttons on the main page. The first one will allow the user to check the what is in front of the door, the second will be used to open a door, the third will be used to to show the user who has access to the door. The fourth used to see who last used the door and finally the last button shows the application credits | • The first button allows the user to access the camera to see what is at the door • Second butto opens the door • Thord button shows a list of user • Fourth button show who last used the door • Credits button, when pressed, brings to the activity containing the collaborators information
FE-2 | Credits Button | As a presenter, I would like to have the ability to select the credits button on the main page so that I see who collaborated on the application. (Story) | 1 | Sprint 1 | Completed | The credit button will lead the presenter to another activity containing the information regarding the collaborators of the application | • Credits button, when pressed, brings to the activity containing the collaborators information
BE-1 | Profile | As a user, I want to be able to create a profile so that I can myself as an administrator. (Story) | 3 | Sprint 1 | Completed | The presenter should be able to create a profile. | • Create a profile
GEN-1 | Login Page | As a presenter, I want to be able to login so that I can have access to the application's functionnalities. (Story) | 3 | Sprint 1 | Completed | The presenter should be able to create a profile if they don't have one and be able to login once they have one. | • Create an account and login
GEN-2 | Display History | As a presenter, I want to check the history of the usage of the door to see who had previously showed up at my door. (Story) | 5 | Sprint 1 | Completed | The application monitors and registers those who have unlocked the door, it display the pictures took once the user clicks the History button | • Display a list of pictures when History is clicked
BE-3 | Setup Database | As a user, I want my admin profile, history, and pictures to be saved on database so that I can easily access them anywhere | 3 | Sprint 1 | Completed | The user's profile should be saved in a database, using Firebase. | • Able to add a profile to the database • Able to get the profile from the database
BE-2 | Connect Sensor to Application | As a presenter, I want the motion sensor detect if anyone is at the door and send a notification delivered in history activity (Epic) | 3 | Sprint 2 | Completed | The motion sensor notifies me when someone is at the door by detecting something with the motion sensor. | • Sensor is connected • Sensor is detecting movement and sending a notification to the application
GEN-3 | Wifi Connected | As a presenter, I want to know when the application is not connected to Wifi so that I can connect it manually. (Story) | 8 | Sprint 2 | Completed | The presenter wants to always know if the board is connected to the phone. If it is not connected, the application will bring the presenter to another activity that will allow him/her to connect to the board. | • Check if the board is connected to the phone • If the sensor is not connected, bring the user to the connection activity
BE-4 | Connect Camera to Application | As a presenter, I want to be able to see who is at the door to allow or deny access. (Story) | 5 | Sprint 2 | Completed | The camera should capture the view in front of the door if the motion sensor detects movement. | • Camera is connected • Camera takes a picture if sensor detects movement
BE-5 | Unlock Door | As a presenter, I want the ability unlock the door electronically (Story) | 5 | Sprint 2 | Completed | The presenter will be able unlock the door and open it. | • Clicking button unlocks the door
FE-3 | List of Users | As a presenter, I want the ability to view all the people who have access to the controls of application by clicking Administrators to see who has the same privilleges as me. (Story) | 5 | Sprint 2 | Completed | Once the button is pressed, the user is sent to a screen showing authorized users. | • Display a list of all authorized users
GEN-10 | Modify Profile | As an user, I want be able to modify values in my profile to represent my present reality. (Story) | 2 | Sprint 2 | Completed | The user should be directed to a profile page to change her username, email, or password. | • Be able to peek and unlock multiple doors
GEN-4 | Peek Door Button | As a presenter, I want the ability to see who is at the door when the motion sensor is activated and notifies me using the first button to allow me to permit or deny entrance. (Story) | 3 | Sprint 2 | Completed | The Peek Door button will allow the user to access a camera and see who is at the door. | • Be able to view through a camera after pressing the button
GEN-11 | Refactor Display History | As an user, I want be able to view the history of people who attempted to open the door in descending chronological order to know who was a the door. (Story) | 3 | Sprint 2 | Completed | The user should be viwing images taken by the camera in descending orer chronologically, only the Firebase strorage should be used. | • Be to retrieve images from the storage in descending order of date without using Cloud Firestore
GEN-12 | RFID | As a .user, I want the ability to unlock my door even when there is no internet connection to be able to open my door during extreme weather conditions. | 3 | Sprint 2 | Completed | The RFID should allow the user to unlock the door without using the Android application. | • Unlock the door using RFID
BE-6 | Reset Password | As an user, I want to be able to reset my password through my email to grant me access to the apllication in case of forgetting my password. (Story) | 5 | Sprint 3 | Completed | The user gets a email, sent by the application, to to reset his password. The new password is then updated on to the database. | • Get email to reset password • Password is stored in the database
GEN-6 | Embedded Door | As an user, I want to have the system already integrated to a door so that it maximizes the responsiveness of the product and minimizes space comsumption. (Epic) | 2 | Sprint 3 | Completed | The should have a door which can use the functionnalities of our application, by creating an embedded system on a door. | • Have a door which works with the application
GEN-7 | Lock for Door | As an user, I want to have a lock on my door which is responsive to the applcaition to allow me to prevent intrusion. (Story) | 2 | Sprint 3 | Completed | The lock should be embedded on the door and be rsponsive to commnads coming from the application. | • Lock is on the door • Lock respond to application
GEN-8 | Camera Holder | As an user, I want camera to be fixed near the door to take pictures of anything in front of it. (Story) | 2 | Sprint 3 | Completed | The motion sensor notifies me when someone is at the door by detecting something with the motion sensor. | • Sensor is connected • Sensor is detecting movement and sending a notification to the application
GEN-9 | Rasberry -Pi Holder | As an user, I want circuits to be embedded on the door for minimal space usage. (Story) | 2 | Sprint 3 | Completed | The motion sensor notifies me when someone is at the door by detecting something with the motion sensor. | • Sensor is connected • Sensor is detecting movement and sending a notification to the application
FE-4 | Embellish Application | As an user, I want to have a friendly graphical user interface to understand easily what the application does. (Story) | 1 | Sprint 3 | Completed | The user should have in front of him an easy to understand application with decorative backgrounds to appeal to the larger public . | • Confirmation from the stakeholders
EX -2 | Facial Recognition | As an administrator, I want the app to scan the picture of me it took at the door so that it verifies that I am an admin and unlock the door automatically for me. (Epic) | 8 | Sprint 3 | Completed | The camera takes picture of the person at the door and scans if it is an administrator. Open the door if it is, else lock the door. | • The pictures taken are scanned • The software distinguishes an administrators from others • The only opens for administrators after verification
GEN-13 | Refactor Peek Door | As an administrator, I want a responsive application to see who is at my door within seconds. (Story) | 2 | Sprint 3 | Completed | Peek Door should not sort all the images from a directory, rather use a given image url. | • Peek Door should use the image url of its door • Peek Door should still function
GEN-14 | Refactor Unlock Door | As an administrator, I want a responsive application to unlock my door within seconds. (Story) | 2 | Sprint 3 | Completed | The code fro Rasberry-Pi should be clean and efficient. | • Code should be clean and efficient • Unlock Door should still function
GEN-17 | Refactor Edit Profile | As an administrator, I want a responsive application to update my profile within seconds. (Story) | 2 | Sprint 3 | Completed | Edit Proifle code shpuld be clean and readable. Any useless code should be removed and effcient solution should be found. | • Code should be clean and efficient • Edit Profile should still function
GEN-16 | Notification when someone is at the door | As an administrator, I want to get a notification when someone is at my door so that I can be readily available to open the door or deny access. (Story) | 3 | Sprint 3 | Completed | Send a notification to the user when a new picture is taken and stored in the proper directory. | • Send a notifictaion when a new picture appears in the storage
GEN-5 | Open Door Button | As a presenter, I want the ability to select the Open Door button to access the door without being physically there to save time and energy. (Epic) | 3 | Future | Not in sprint | The button allows the user to open the door without his or her presence. | • Clicking the button, opens the door
EX-1 | Gesture | As an user, I want to be able to open the door using a gesture sensor using bluetooth and within a close range to minimize the range and mouvements needed to open a door. (Epic) | 13 | Future | Not in sprint | The gesture sensor opens the door for the user when used | • The door opens with gestures
EX-3 | Monitor Admin's Entry | As an administrator, I want the the history page to also record the user's device that open the door so that I can monitor which administrators opens the door (Epic) | 3 | Future | Not in sprint | The app shows which administrator has opened the door. | • The history page shows the admin who opened the door along with the user that was at the door
EX-4 | Refactor History | As an administrator, I want a responsive application to see the list of people who were at my door. (Story) | 5 | Future | Not in sprint | The app shows which administrator has opened the door. | • The history page shows the admin who opened the door along with the user that was at the door
EX-5 | Multiple Doors | As an administrator, I to be able to access multiple doors per account so that I can manage my doors appropriately. (Epic) | 5 | Future | Not in sprint | The database should allow the user to egister multiple doors per profile. Redo the datastructure of the profiles in the database. Unlock door shows a list of doors to unlock | • Unlock doors show multiple doors to the user • Unlocks the appropriate door when button is clicked
GEN-15 | Delete Users | As an user, I want to be able remove others from the list of users to deny access to unwanted users. (story) | 3 | Future | Not in sprint | Allows users to delete other unwanted usersusing a voting system. | • Deleted users should not be able to access the door • An user is only deleted if al of the mebers of that door vote him out other than himself
EX-6 | Voice Recognition | As an user, I want to be able to open my door using voice recognition to open the door with minimal actions. (Epic) | 13 | Future | Not in sprint | Use voice recognition to enable the door to open, store the voice of the user in the database. | • If the voice of the user is registered to that door, open the door, else the door is locked
EX-7 | Bell | As an user, I want to be able to use a bell to notify the owner that I am in front of the door. (Story) | 13 | Future | Not in sprint | The door should have a bell connected to it to notify the administrator when it is pressed that a person is at the door. The camera take a picture of that person. | • Bell pressed should send a notification to the applcaition and a picture should be taken
EX-8 | Live Streaming | As an user, I want to be able to see the live events happening in front of my door. It would then allow me to know what is going on in its surroundings (Epic) | 8 | Future | Not in sprint | The camera should be able to live stream the environment in front of the door and show the user in peek door the footage. | • When Peek Door is pressed, a live footage of the front of the door is shown
EX-9 | Motion Sensor Check | As an user, I want the door to not send a notification when the motion sensor is triggered, but not by a person to minimize the number of false alarms. (Story) | 8 | Future | Not in sprint | Whenever a picture is taken because the motion sensor is triggered, an AI analyzes the picture to determine if it is a flase alram or not. | • When the motion snesor is triggered by something other than a person, no notification is sent • When the motion snesor is triggered by a person, a notification is sent
EX-10 | Keypad | As an user, I want a keypad to allow me to open my door as if I lose my RFID card and power is cut off, I would still be able to unlock my door . (Story) | 5 | Future | Not in sprint | A 4 digit-pin should allow the user to unlock their door. | • If the user enters the correct 4 digits, the door unlocks, else it remains locked
EX-11 | Detect if it is a Human at the door | As an user, I want the the camera to detect if it is a human at the door and only send notifications if it is verified so that I do not always receive notfications when an animals or object passes the motion sensor(Story) | 13 | Future | Not in sprint | Computation should done by the AI to detect if object is a human | • AI detects succesfully when the object is a human. • Does not send notification if object is not a human
EX-12 | Automatic Door Closer | As an user, I want my door to close by itself or be kept open if I want so as to prevent any intruders and make carrying of load through the door easier. (Story) | 1 | Future | Not in sprint | The door should have a door closer on top of it so that it closes itself gradually whenever it is open. | • Door gradually closes by itself without the intervention of anyone
EX-13 | Notify if door is open | As an user, I want to install a magnetic switch at the door so that I can be notified if my door is still open after 1 min and then close it. (Story) | 3 | Future | Not in sprint | Send a notification to the user if the door has not being locked after 1 min | • Send a notifictaion when the door has been left open after 1 min
EX-14 | Button to open the door from inside | As an user, I want to be able to open my door from inside by pressing a button so I have can exit my house easily. (Story) | 2 | Future | Not in sprint | There should be a button beside the door so that the door can be unlocked when pressed | • The door unlocks when the button is pressed
EX-15 | Nofication of access to house by alternative means | As an user, I want to be notified when other means of entry like RFID and Door code is used to gain access to my house so that I can monitor who comes in to the house. (Story) | 3 | Future | Not in sprint | Send a notification to the user if the door was opened by RFID or door code | • Send a notifictaion when the door has been open by RFID or door code

## Sprint 1
Sprint 1 Backlog
Sprint 1 Goal(s): Start the Applicationès Skeleton, Create Database, Coding and Testing of Sensors for Arduino
Total ideal Hours: |  | 78
Story ID | Task ID | Task Title | Task Description | Ideal Hours |  | Status | Comments
FE-1 | FE-1 | Main Page Button | There will be 5 buttons on the main page. The first one will allow the user to check the what is in front of the door, the second will be used to open a door, the third will be used to to show the user who has access to the door. The fourth used to see who last used the door and finally the last button shows the application credits. (See Documentation/Layout_Pictures/main_page) | 2 | hrs | Completed | Assigned to: Irfan Ahmed Priority 1 Done: Main Page contains all 5 buttons
FE-2 | FE-2 | Credits Button | The credit button will lead the presenter to another activity containing the information regarding the collaborators of the application | 2 | hrs | Completed | Assigned to: Irfan Ahmed Priority 5 Done: Credits contain infromation on project engineer and devlopers
GEN-2 | GEN-2.1 | Display History | Displays pictures taken by the camera in History page. | 5 | hrs | Completed | Assigned to: Alec Kurkdjian Priority 3 Done: After clicking History, gets pictures uploaded to database and puts them in a list
BE-1 | BE-1 | Profile | Profile of admins should contain: username, email, password, identifier of door, and a list of admins who have access to the same door. | 3 | hrs | Completed | Assigned to: Alec Kurkdjian Priority 1 Done: Completed a profile class which encompass everything needed fro an user
GEN-1 | GEN-1.1 | Login Page | The presenter should be able to create a profile if they don't have one and be able to login once they have one by entering an door identifier, email address, password, and username. | 5 | hrs | Completed | Assigned to: Cong-Vinh Vu Priority 2 Done: Allow the user to sign up and log in
GEN-1 | GEN-1.2 | Login Page | If the user creates a profile, check for valid name and password. | 1 | hrs | Completed | Assigned to: Cong-Vinh Vu Priority 2 Done: Does not allow invalid inputs in username, email, password and door identifier fields
BE-3 | BE-3.1 | Learn Firebase | Learn how to use Firebase. | 5 | hrs | Completed | Assigned to: Alec Kurkdjian & Cong-Vinh Vu Priority 1 Done: be able to create a dtabase class
BE-3 | BE-3.2 | Storing Pictures in Database | Learn how to store pictures into a database. | 5 | hrs | Completed | Assigned to: Alec Kurkdjian & Cong-Vinh Vu Priority 2 Done: Able to store pictures inside the database
BE-3 | BE-3.3 | Setup Database | The user's profile should be saved in a database, using Firebase. | 5 | hrs | Completed | Assigned to: Alec Kurkdjian & Cong-Vinh Vu Priority 1 Done: Create a databaseHelper class and be able to uplaod and retrieve information from it
BE-2 | BE-2.1 | Learn Arduino for Sensor | Investigate how to use Aduino and use the I/O ports. Check the analog and digital I/O ports. | 5 | hrs | Completed | Assigned to: Shadi Makdissi & Ogo-Oluwa Jesutomi Olasubulumi Done: Get data from the sensors
BE-2 | BE-2.2 | Motion Sensor | Learn the behaviour of the senors, inputs and outputs. | 5 | hrs | Completed | Assigned to: Shadi Makdissi , Ogo-Oluwa Jesutomi Olasubulumi ,& Irfan Ahmed Done: Able to test and adjust the range of the sensor
BE-2 | BE-2.3 | Connect Sensor to Arduino Board | The Arduino should be able to receive the data from the sensor. | 5 | hrs | Completed | Assigned to: Shadi Makdissi & Ogo-Oluwa Jesutomi Olasubulumi Done: Able to use the serial monitor
BE-2 | BE-2.4 | Coding Arduino Sensor | Coding Arduino to send and receive signals from the sensor using thresholds. | 5 | hrs | Completed | Assigned to: Shadi Makdissi & Ogo-Oluwa Jesutomi Olasubulumi Done: Get signals from the sensor
BE-2 | BE-2.5 | Coding Wifi Sensor | Coding Arduino to send signals using Wfi. | 5 | hrs | Completed | Assigned to: Shadi Makdissi & Ogo-Oluwa Jesutomi Olasubulumi Done: Control the LEDs with Wifi server
BE-4 | BE-4.1 | Connect Camera to Arduino Board | The Arduino should be able to receive the data from the camera. | 5 | hrs | Completed | Assigned to: Shadi Makdissi & Ogo-Oluwa Jesutomi Olasubulumi Done: Receive the image from the camera
BE-4 | BE-4.2 | Coding Arduino Camera | Coding Arduino to send and receive signals from camera. | 5 | hrs | Completed | Assigned to: Shadi Makdissi & Ogo-Oluwa Jesutomi Olasubulumi Done: Receive electrical signals from the camera
BE-4 | BE-4.3 | Learn Arduino | Learning how to use an Arduino Board | 5 | hrs | Completed | Assigned to: Irfan Ahmed Done: Read documentation on Arduino board
BE - 4 | BE-4.4 | Coding Lock | User shold be able to control the power going into the lock with the help of arduino and a relay | 5 | hrs | Completed | Assigned to: Irfan Ahmed Done: Able to control the lock's mechanism

## Sprint 2
Sprint 2 Backlog
Sprint 2 Goal(s): Hardware Communication with Database and Finish Login Page, History Page, Administartors Page, Unlock Door and, Peek Door
Total ideal Hours: |  | 78
Story ID | Task ID | Task Title | Task Description | Ideal Hours |  | Status | Comments
BE-2 & BE-4 | BE-2.4.1 | Connectionof Rasberry -Pi Wifi | Rasberry -Pi and wifi should be connected with good communication between both devices. | 2 | hrs | Completed | Priority 1
F3-3 | F3-3 | List of Users | Once the button is pressed, the user is sent to a screen showing authorized users. | 5 | hrs | Completed | Priority 1
GEN-1 | GEN-1.3 | Login Page | Refactor the Login and Sign Up functionnalities. | 2 | hrs | Completed | Priority 1
GEN-1 | GEN-1.4 | Login Page | The application should not allow two duplicate users inside the database. | 3 | hrs | Completed | Priority 1
GEN-1 | GEN-1.5 | Login Page | The application should not allow the usage of same emails and usernames. | 3 | hrs | Completed | Priority 1
GEN-2 | GEN-2.2 | Display History | Refactor the Display History functionnalities. | 2 | hrs | Completed | Priority 1
GEN-2 | GEN-2.3 | Display History | Use Cloud Firestore to store data instead of Firebase's Real Time Database. | 3 | hrs | Completed | Priority 1
BE-5 | BE-5 | Unlock Door | The presenter will be able unlock the door and open it. | 5 | hrs | Completed | Priority 2
GEN-4 | GEN-4 | Peek Door Button | The Peek Door button will allow the user to access a camera and see who is at the door. | 3 | hrs | Completed | Priority 2
BE-2 & BE-4 | BE-2.4.1 | Multiple Sensors | All sensors should be able to work simultaneously when connected together. | 5 | hrs | Completed | Priority 2
GEN-10 | GEN-10 | Modify Profile | Create a profile page and allow user to modify their credentials. | 4 | hrs | Completed | Priority 2
GEN-7 | GEN-7.2 | Instructions from Database | Rasberry-Pi should be able to take instructions from Firebase and implement it. | 5 | hrs | Completed | Priority 2
GEN-7 | GEN-7.3 | Instructions to Database | The application should be able to send instructions to the database. | 3 | hrs | Completed | Priority 2
BE-2 & BE-4 | BE-2.4.1 | Connect Rasberry-Pi Database | Rasberry-Pi should be able to connect to the firebase server. | 5 | hrs | Completed | Priority 2
GEN-3 | GEN-3 | Wifi Connected | The user should be notified if they are not connected to the internet. | 5 | hrs | Completed | Priority 3
BE-4 | BE-4.5 | Coding Wifi Camera | Coding Rasberry-Pi to send camera pictures to Wifi server. | 5 | hrs | Completed | Priority 3
BE-4 | BE-4.6 | Camera Pictures to Database | Rasberry-Pi should be able to send pictures to Firebase. | 5 | hrs | Completed | Priority 3
GEN-12 | GEN-12 | RFID | Unlocks the lock when card is near the sensor. | 4 | hrs | Completed | Piority 4
TEST | TEST-1 | Testing Sign Up | Testing and validation sign up page. | 1 | hrs | Completed | Priority 5
TEST | TEST-2 | Testing Login | Testing and validation login page. | 1 | hrs | Completed | Priority 5
TEST | TEST-3 | Testing Peek Door | Testing and validation of peek door button and activty. | 1 | hrs | Completed | Priority 5
TEST | TEST-4 | Testing Unlock Door | Testing and validation of unlock door | 1 | hrs | Completed | Priority 5
TEST | TEST-5 | Testing History | Testing and validation of history activity. | 1 | hrs | Completed | Priority 5
TEST | TEST-6 | Testing Administartors | Testing and validation of administrators pages. | 1 | hrs | Completed | Priority 5
TEST | TEST-7 | Testing Edit Profile | Testing and validation of edit profile feature. | 1 | hrs | Completed | Priority 5
WR | WR-1 | Product Backlog and Sprint Grooming | Groming of Sprint 3 and Product Backlog. Update Sprint 2. | 2 | hrs | Completed | Priority 5
WR | WR-2 | Testing Documents | Follow the test plans and template. | 2 | hrs | Completed | Priority 5
WR | WR-3 | Definition of Done | Follow template on Moodle. | 2 | hrs | Completed | Priority 5
WR | WR-4 | Team Blog | Follow template and discuss during team meetings. | 2 | hrs | Completed | Priority 5

## Sprint 3
Sprint 3 Backlog
Sprint 3 Goal(s): Finish the entire application, add extra features such as facial recognition, have the physical door present, and embellish our product
Total ideal Hours: |  | 71
Story ID | Task ID | Task Title | Task Description | Ideal Hours |  | Status | Comments
GEN-7 | GEN-7.1 | Add Lock | The lock system should be installed on the door. | 2 | hrs | Planned | Priority 1
GEN-16 | GEN-16 | Notification | As an administrator, I want to get a notification when someone is at my door so that I can be readily available to open the door or deny access. (Story) | 5 | hrs | Planned | Priority 1
BE-6 | BE-6.1 | Reset Password | The application should send an email to the user after clicking I Forgot My Password, to allow the user to reset their own password. | 5 | hrs | Planned | Priority 1
BE-6 | BE-6.2 | Reset Password | The new password entered by the user should be saved into the database, replacing the old one. | 5 | hrs | Planned | Priority 1
GEN-13 | GEN-13 | Refactor Peek Door | Peek Door should not sort all the images from a directory, rather use a given image url. | 5 | hrs | Planned | Priority 2
GEN-6.1 | GEN-6.1 | Building Prototype Door | The prototype door to be used for testing should be built. | 5 | hrs | Planned | Priority 2
GEN-14 | GEN-14 | Refactor Unlock Door | The code fro Rasberry-Pi should be clean and efficient. | 5 | hrs | Planned | Priority 3
GEN-17 | GEN-17 | Refactor Edit Profile | Edit Proifle code shpuld be clean and readable. Any useless code should be removed and effcient solution should be found. | 3 | hrs | Planned | Priority 3
GEN-8 | GEN-8 | Camera Holder | A 3D-printed model to be made to hold the camera. | 2 | hrs | Planned | Priority 3
GEN-9 | GEN-9 | Rasberry-Pi Holder | A 3D-printed model to be made to hold the Rasberry-Pi by the door. | 2 | hrs | Planned | Priority 3
FE-4 | FE-4 | Embellish Application | The design of the app should be updated to the desired design. | 3 | hrs | Planned | Priority 4
EX-2 | EX-2.1 | Facial Recognition | We need to take many pictures and the AI needs to be trained to have an adequate success rate. | 5 | hrs | Planned | Priority 4
EX-2 | EX-2.2 | Facial Recognition | The camera takes picture of the person at the door and scans if it is an administrator. Open the door if it is, else lock the door. | 5 | hrs | Planned | Priority 4
TEST | TEST-1 | Testing Sign Up | Testing and validation sign up page. | 1 | hrs | Planned | Priority 5
TEST | TEST-2 | Testing Login | Testing and validation login page. | 1 | hrs | Planned | Priority 5
TEST | TEST-3 | Testing Peek Door | Testing and validation of peek door button and activty. | 1 | hrs | Planned | Priority 5
TEST | TEST-4 | Testing Unlock Door | Testing and validation of unlock door | 1 | hrs | Planned | Priority 5
TEST | TEST-5 | Testing History | Testing and validation of history activity. | 1 | hrs | Planned | Priority 5
TEST | TEST-6 | Testing Administartors | Testing and validation of administrators pages. | 1 | hrs | Planned | Priority 5
TEST | TEST-7 | Testing Edit Profile | Testing and validation of edit profile feature. | 1 | hrs | Planned | Priority 5
TEST | TEST-8 | Testing AI | Testing and validation facial recognition feature. | 2 | hrs | Planned | Priority 5
TEST | TEST-9 | Testing Reset Password | Testing and validation of reset password functionnality. | 1 | hrs | Planned | Priority 5
TEST | TEST-10 | Testing Open Door | Testing and validation of edit profile feature. | 1 | hrs | Planned | Priority 5
WR | WR-1 | Product Backlog and Sprint Grooming | Groming of Sprint 3 and Product Backlog. Update Sprint 2. | 2 | hrs | Planned | Priority 5
WR | WR-2 | Testing Documents | Follow the test plans and template. | 2 | hrs | Planned | Priority 5
WR | WR-3 | Definition of Done | Follow template on Moodle. | 2 | hrs | Planned | Priority 5
WR | WR-4 | Team Blog | Follow template and discuss during team meetings. | 2 | hrs | Planned | Priority 5
WR | WR-5 | Final Report | Do final report. | 4 | hrs | Planned | Priority 5
WR | WR-6 | User Manual | Manual to show to the user how to use or application along side the hardware. | 3 | hrs | Planned | Priority 5