## Sheet1
[6 empty] | Team Members | [9 empty] | Instructions: Fill in only green portions. For the activities table put number 1 in the square under each name if that individual participated in that activity. The number of hours for each individual will be calculated automatically. Readjust cell size to be sure all text is visible as needed.
[6 empty] | First Name | Last Name | Nickname (max 6 characters)
[6 empty] | Irfan | Ahmed | A.I
[6 empty] | Alec | Kurkdjian | Alec
[6 empty] | Cong-Vinh | Vu | CV
[6 empty] | Shadi | Makdissi | Shadi
[6 empty] | Ogo Oluwa | Jesutomi olasubulumi | Tomi
Add more rows as necessary
Activities Table
Date | Who |  |  |  |  | Type of Activty | Number of hourse spent | Purpose | Output | Hours spent
| A.I | Alec | CV | Shadi | Tomi |  |  |  |  | A.I | Alec | CV | Shadi | Tomi
Milestone 1
2019-09-05 | 1 | 1 | 1 | 1 | 1 | Meeting | 1 | Discuss about how we will manage our code and where it will be available for all member of the teams | We decided to use GitHub to store our documentation and code for the project | 1 | 1 | 1 | 1 | 1
2019-09-09 | 1 | 1 | 1 | 0 | 1 | meeting | 2 | Brainstorm ideas and come up with 6 opportunity statement | Came up with 6 ideas and opportunity statements | 2 | 2 | 2 | 0 | 2
2019-09-14 | 1 | 0 | 1 | 1 | 1 | Voice Call meetin | 2 | Create a WOT analysis of our 6 opportunity statement | Finished ranking our opportunity statement through a WOT analysis | 2 | 0 | 2 | 2 | 2
2019-09-19 | 1 | 1 | 1 | 1 | 1 | Meeting | 1 | Set Mission Statement | Finished writing down our mission statement for the chosen opportunity statement | 1 | 1 | 1 | 1 | 1
2019-09-21 | 1 | 1 | 1 | 1 | 1 | Voice Call meeting | 1 | Finalise report for Milestone 1 | We finished setting up our milestone 1 report in a word document | 1 | 1 | 1 | 1 | 1
[9 empty] | Total hours | 7 | 5 | 7 | 5 | 7
[9 empty] | Total team hours | [5 empty] | 31
Milestone 2 | [9 empty] | A.I | Alec | CV | Shadi | Tomi
2019-10-01 | 1 | 1 | 1 | 1 | 1 | Voice Call meeting | 1 | Divide Milestone 2 task | Everyone has been assigned a specefic task related to milestone 2 | 1 | 1 | 1 | 1 | 1
2019-10-04 | 1 | 1 | 1 | 1 | 1 | Face to face meeting with stakeholder 1 | 1 | Interview with stakeholder 1 | Gathered information on stakeholder 1 and his point of view on our product | 1 | 1 | 1 | 1 | 1
2019-10-05 | 1 | 1 | 1 | 1 | 1 | Face to face meeting with stakeholder 2 | 1 | Interview with stakeholder 2 | Gathered information on stakeholder 1 and his point of view on our product | 1 | 1 | 1 | 1 | 1
2019-10-07 | 1 | 1 | 1 | 1 | 1 | Meeting | 1 | Finalise report for Milestone 2 | We finished setting up our milestone 2 report in a word document | 1 | 1 | 1 | 1 | 1
[9 empty] | Total hours | 4 | 4 | 4 | 4 | 4
[9 empty] | Total team hours | [5 empty] | 20
Sprint 1 | A.I | Alec | CV | Shadi | Tomi |  |  |  |  | A.I | Alec | CV | Shadi | Tomi
2019-10-11 | 1 | 1 | 1 | 1 | 1 | Voice call meeting | 1 | Prepare sprint 1 backlog and goals | We finished setting up our product backlog and sprint 1 backlog | 1 | 1 | 1 | 1 | 1
2019-10-16 | 1 | 1 | 1 | 1 | 1 | Voice call meeting | 0.25 | To get up to date of the team progress and the task each member is working on | We got up to date on which task is being done by which teamates | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
2019-10-18 | 1 | 1 | 1 | 1 | 1 | Voice call meeting | 0.25 | To get up to date of the team progress and the task each member is working on | We got up to date on which task is being done by which teamates | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
2019-10-19 | 0 | 1 | 0 | 0 | 0 | Display History | 5 | I want to check the history of the usage of the door to see who had previously showed up at my door. | Alec was able to view history of people at the door | 0 | 5 | 0 | 0 | 0
2019-10-19 | 0 | 1 | 0 | 0 | 0 | Create Profile on database | 3 | As a user, I want to be able to create a profile so that I can myself as an administrator. (Story) | Alec was able to create profiles for any user | 0 | 3 | 0 | 0 | 0
2019-10-19 | 0 | 1 | 1 | 0 | 0 | Learning firebase, setting up firebase & sending pics to firebase | 13 | As a user, I want my admin profile, history, and pictures to be saved on database so that I can easily access them anywhere | Database was created and Pictures were stored | 0 | 6 | 7 | 0 | 0
2019-10-20 | 0 | 0 | 1 | 0 | 0 | Create Profile on on app and sign-in | 6 | Users can create new profile and sign in to the app so they can access contents of the app | Users can create new profile and sign in to the app | 0 | 0 | 6 | 0 | 0
2019-10-21 | 1 | 1 | 1 | 1 | 1 | Meeting in EV | 2 | Test out the log in/sign up page, home page and display history of the app. | The functionality are working and have found some points to improve | 2 | 2 | 2 | 2 | 2
2019-10-23 | 1 | 0 | 0 | 1 | 1 | Learning sensors | 30 | Being able to use these sensors for the project | learnt how to use the sensors and knowing the pinouts and writing codes to test them | 3 | 0 | 0 | 13.5 | 13.5
2019-10-24 | 1 | 1 | 1 | 1 | 1 | Voice call meeting | 0.25 | To get up to date of the team progress and the task each member is working on | We got up to date on which task is being done by which teamates | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
2019-10-24 | 1 | 0 | 0 | 0 | 0 | Coding Lock | 2 | user should be able to unlock the door electronically | Irfan was able to complete the code for locking and unlocking of the door lock on arduino | 2 | 0 | 0 | 0 | 0
2019-10-24 | 1 | 0 | 0 | 0 | 0 | Main page and Credits button | 3 | Creating the main page where user | Irfan completed the main page and credits button of the app | 3 | 0 | 0 | 0 | 0
2019-10-24 | 1 | 0 | 0 | 0 | 0 | learning Arduino | 2 | Having a understanding of how arduino works | Irfan was able to learn how to use arduino boards | 2 | 0 | 0 | 0 | 0
2019-10-25 | 1 | 0 | 0 | 1 | 1 | Meeting in the lab room | 2 | Test the connection of the sensors with arduino | We were able to take picture and unlock the door with a motion sensor | 2 | 0 | 0 | 2 | 2
2019-10-26 | 1 | 1 | 1 | 1 | 1 | Voice call meeting | 1 | Start/verify the sprint 1 document and product backlog grooming | We finished writing/setting up our milestone 2 report in a word document and finished updating our product backlog | 1 | 1 | 1 | 1 | 1
2019-10-27 | 1 | 1 | 1 | 1 | 1 | Voice call meeting | 1.5 | Sprint 2 backlog, sprint 2 goals and deciding what to demo for the meating with the scrum master | We finished setting up our sprint 2 backlog, goals and decided what to demo | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
[9 empty] | Total hours | 18.25 | 20.25 | 19.25 | 21.75 | 21.75
[9 empty] | Total team hours | [5 empty] | 101.25
Sprint 2 | A.I | Alec | CV | Shadi | Tomi |  |  |  |  | A.I | Alec | CV | Shadi | Tomi
2019-10-30 | 1 | 1 | 1 | 1 | 1 | Voice call meeting | 1 | To get up to date of the team progress and the task they are working on. Also divide task for the sprint 2 document | We got up to date on which task is being done by which teamates and divided the documantion part with each other | 1 | 1 | 1 | 1 | 1
2019-11-01 | 1 | 1 | 1 | 1 | 1 | Voice call meeting | 0.25 | To get up to date of the team progress and the task each member is working on | We got up to date on which task is being done by which teamates | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
2019-11-01 | 0 | 0 | 0 | 1 | 0 | connection to firebase | 3 | Ensuring communication with firebase so data is received and sent | we were able to send and receive data | 0 | 0 | 0 | 3 | 0
2019-11-02 | 0 | 0 | 1 | 0 | 0 | Login page | 5 | Refactor the login page for users of different doors | Login page was re-edited | 0 | 0 | 5 | 0 | 0
2019-11-02 | 0 | 1 | 0 | 0 | 0 | list of Admin | 5 | Once the button is pressed, the user is sent to a screen showing authorized users. | Every Admin can viewed for a particular door | 0 | 5 | 0 | 0 | 0
2019-11-02 | 0 | 1 | 0 | 0 | 0 | History of people at door | 5 | Display history of people at the door | we were able to see the history of people at the door | 0 | 5 | 0 | 0 | 0
2019-11-02 | 0 | 0 | 0 | 1 | 0 | motion detects movement and takes picture | 5 | Picture of person should be taken when motion is detected | sensor detects motion and camera takes pic | 0 | 0 | 0 | 5 | 0
2019-11-03 | 1 | 0 | 1 | 0 | 0 | Unlock door | 6 | user will be able to unlock door from the app and the raspberry pi unlocks the door | Door unlocks when unlocked through the app | 3 | 0 | 3 | 0 | 0
2019-11-03 | 0 | 1 | 0 | 0 | 0 | Edit profile page | 3 | Allows user to edit their profile password and picture | Users are able to edit their profile password and picture | 0 | 3 | 0 | 0 | 0
2019-11-03 | 0 | 0 | 0 | 0 | 1 | sending pics taken by camera to firebase | 3 | Sending pics to firebase servers so that it can be checked in the history | Pictures were seen in history | 0 | 0 | 0 | 0 | 3
2019-11-04 | 0 | 0 | 0 | 0 | 1 | RFID | 5 | user should be able to use an RFID tag to unlock the door | user can use an RFID tag to unlock the door | 0 | 0 | 0 | 0 | 5
2019-11-04 | 1 | 0 | 0 | 0 | 0 | Testing edit profile,Admin,History | 2 | Testing | Testing completed | 2 | 0 | 0 | 0 | 0
2019-11-04 | 1 | 0 | 1 | 0 | 0 | Testing Sign up and creating new profile | 2 | Testing | Testing completed | 1 | 0 | 1 | 0 | 0
2019-11-05 | 1 | 1 | 1 | 1 | 1 | Meeting in library | 1.5 | Testing the connections of the sensor with raspberryPi and display the picture taken by the raspberry on the display history | We were sucessfully able to make the connection and take/send a picture from raspberryPi to the app | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
2019-11-06 | 1 | 1 | 1 | 1 | 1 | Voice call meeting | 0.25 | To get up to date of the team progress and the task each member is working on | We got up to date on which task is being done by which teamates | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
2019-11-07 | 1 | 1 | 1 | 1 | 1 | Meeting in library | 1 | Testing if the peak door | We were sucessfully able to peak door | 1 | 1 | 1 | 1 | 1
2019-11-07 | 1 | 0 | 0 | 0 | 0 | Team Blog | 2 | Team Blog | Team Blog | 2 | 0 | 0 | 0 | 0
2019-11-07 | 0 | 0 | 0 | 1 | 0 | D.O.D | 1 | Definition of Done | Defintion of Done completed | 0 | 0 | 0 | 1 | 0
2019-11-07 | 0 | 0 | 0 | 0 | 1 | Testing unlock door works with app, raspberry pi and checking last person at the door | 2 | Testing | Testing completed | 0 | 0 | 0 | 0 | 2
2019-11-08 | 1 | 1 | 1 | 1 | 1 | Voice call meeting | 1 | Sprint 2 grooming | We updated our product backlog | 1 | 1 | 1 | 1 | 1
2019-11-08 | 1 | 0 | 0 | 0 | 0 | Test Document | 2 | Creating test document | Test document completed | 2 | 0 | 0 | 0 | 0
2019-11-09 | 1 | 1 | 1 | 1 | 1 | Voice call meeting | 1.5 | Finalize and verify the sprint 2 document | We finished setting up our milestone 2 report in a word document | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
2019-11-10 | 1 | 1 | 1 | 1 | 1 | Voice call meeting | 1.5 | Sprint 3 backlog, sprint 3 goals and deciding what to demo for the meating with the scrum master | We finished setting up our sprint 3 backlog, goals and decided what to demo | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
[9 empty] | Total hours | 18 | 21 | 17 | 17 | 18
[9 empty] | Total Team hours | [5 empty] | 91
Sprint 3 | A.I | Alec | CV | Shadi | Tomi |  |  |  |  | A.I | Alec | CV | Shadi | Tomi
2019-11-11 | 1 | 1 | 0 | 0 | 0 | Building Prototype Door | 5 | Building a prototype door | The door was succesfully built | 2.5 | 2.5 | 0 | 0 | 0
2019-11-12 | 1 | 1 | 0 | 0 | 0 | Add lock | 0.5 | Adding the lock in the built door | The lock was succesfully inserted on the door | 0.5 | 0.5 | 0 | 0 | 0
2019-11-13 | 0 | 0 | 1 | 0 | 0 | Time out for sign up | 4 | The user will be timeout from signing in after numerous failed attempt to sign up with a Door ID | The user is blocked from further signing in after 3 failed attemps for an hour | 0 | 0 | 4 | 0 | 0
2019-11-13 | 1 | 1 | 1 | 1 | 1 | Voice call meeting | 0.25 | To get up to date of the team progress and the task each member is working on | We got up to date on which task is being done by which teamates | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
2019-11-13 | 0 | 1 | 0 | 0 | 0 | Forgot Password | 10 | Adding a forget password option on the log in page that send the user their username and passowrd via sms | The forget password features has succesfully been added to the log in page and sends a sms message | 0 | 10 | 0 | 0 | 0
2019-11-13 | 0 | 0 | 0 | 1 | 0 | 3d print camera holder | 3 | To print a stand for the camera on the door | The camera holder was sucessfully printed | 0 | 0 | 0 | 3 | 0
2019-11-14 | 0 | 0 | 1 | 0 | 0 | Notification | 5 | Adding a notification message when motion sensor is triggered | Notification is send to the user when motion detected | 0 | 0 | 5 | 0 | 0
2019-11-14 | 0 | 0 | 0 | 0 | 1 | 3d print rasberry-pi | 3 | To print a stand for the rasberry-pi on the door | The rasberry-pi holder was succesfully printed | 0 | 0 | 0 | 0 | 3
2019-11-15 | 0 | 0 | 0 | 0 | 1 | embellish application | 3 | The design of the app should be updated to the desired design. | The proper design for the application was decided | 0 | 0 | 0 | 0 | 3
2019-11-16 | 0 | 0 | 0 | 1 | 0 | Wiring | 5 | Fixing the wiring for the connections between rasberry pi and sensors/actuator | Wires were succesfully connected and propoerly labeled in case it gets disconnected | 0 | 0 | 0 | 5 | 0
2019-11-17 | 0 | 0 | 1 | 0 | 0 | Refactor Peek Door | 5 | The code for the check door should be clean and efficient | The code for check door has been optimized | 0 | 0 | 5 | 0 | 0
2019-11-17 | 0 | 1 | 0 | 0 | 0 | Refactor edit profile | 2 | The code for the edit profile should be clean and efficient | The edit has been optimized | 0 | 2 | 0 | 0 | 0
2019-11-18 | 1 | 0 | 0 | 0 | 0 | Refactor unlock door | 3 | The code for the unlock door should be clean and efficient | The unlock door code has been optimized | 3 | 0 | 0 | 0 | 0
2019-11-20 | 0 | 0 | 0 | 0 | 1 | facial recognition | 10 | To unlock the door via facial recognition | The facial recognition was succesfully added | 0 | 0 | 0 | 0 | 10
2019-11-21 | 1 | 0 | 0 | 0 | 0 | Test sign up | 1 | Testing if the sign up features work | The sign up works | 1 | 0 | 0 | 0 | 0
2019-11-21 | 1 | 0 | 0 | 0 | 0 | Test login | 1 | Testing if the login features work | The login works | 1 | 0 | 0 | 0 | 0
2019-11-21 | 1 | 0 | 0 | 0 | 0 | Test check door | 1 | Testing if the check door features work | the check door works | 1 | 0 | 0 | 0 | 0
2019-11-21 | 1 | 0 | 0 | 0 | 0 | Test unlock door | 1 | Testing if the unlock door features work | unlock door works | 1 | 0 | 0 | 0 | 0
2019-11-21 | 0 | 0 | 0 | 1 | 0 | Test history | 1 | Testing if the display history features work | test history works | 0 | 0 | 0 | 1 | 0
2019-11-21 | 0 | 0 | 0 | 1 | 0 | Test administrators | 1 | Testing if the display admi work | displaying administrators works | 0 | 0 | 0 | 1 | 0
2019-11-21 | 0 | 0 | 0 | 1 | 0 | Test edit profile | 1 | Testing if the edit profile features work | edit profile works | 0 | 0 | 0 | 1 | 0
2019-11-21 | 0 | 0 | 0 | 0 | 1 | Test AI | 1 | Testing if facial recognition features work | Facial recognition works | 0 | 0 | 0 | 0 | 1
2019-11-21 | 0 | 0 | 0 | 1 | 0 | Test forgot password | 0.5 | Testing if the forgot password features work | Forgot password works | 0 | 0 | 0 | 0.5 | 0
2019-11-21 | 0 | 0 | 0 | 1 | 0 | Testing time out feature | 0.5 | Testing if the time out feature works | Time out features works | 0 | 0 | 0 | 1 | 0
2019-11-22 | 1 | 1 | 1 | 1 | 1 | Voice call meeting | 0.25 | To get up to date of the team progress and the task each member is working on | We got up to date on which task is being done by which teamates | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
2019-11-24 | 1 | 1 | 1 | 1 | 1 | Voice call meeting | 1 | Product backlog grooming | Porduct backlog succesfully grooming | 1 | 1 | 1 | 1 | 1
2019-11-24 | 1 | 1 | 1 | 1 | 1 | Voice call meeting | 1 | Plan who will be presenting and how we are going to do the final presentation | Decided who will be the one presenting and how we will demo our prodcut | 1 | 1 | 1 | 1 | 1
2019-11-26 | 1 | 0 | 0 | 0 | 0 | Testing document | 2 | Create the test document | Test document completed | 2 | 0 | 0 | 0 | 0
2019-11-27 | 0 | 1 | 0 | 0 | 0 | Ethical issue | 1 | Write up the ethical issue reguarding our application | Ethical issue component completed | 0 | 1 | 0 | 0 | 0
2019-11-27 | 0 | 0 | 0 | 1 | 0 | Definition of Done | 2 | Create the definition of done table | Definition of done completed | 0 | 0 | 0 | 2 | 0
2019-11-27 | 1 | 0 | 0 | 0 | 0 | Team blog | 2 | Fill up the team blog stub | Team blog stub completed | 2 | 0 | 0 | 0 | 0
2019-11-28 | 0 | 0 | 1 | 0 | 0 | Computer simulation | 1 | Write up the computer simulation component of the report | Computer simulation component completed | 0 | 0 | 1 | 0 | 0
2019-11-28 | 1 | 0 | 0 | 0 | 0 | User manual | 1.5 | Create user manual for open sesame | User manual completed | 1.5 | 0 | 0 | 0 | 0
2019-11-29 | 1 | 1 | 1 | 1 | 1 | Voice call meeting | 0.5 | Review final report | Final report succesfully reviewed | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
[9 empty] | Total hours | 18.5 | 19 | 18 | 17.5 | 20
[9 empty] | total team hours | [5 empty] | 93
[9 empty] | Total hour over project | 65.75 | 69.25 | 65.25 | 65.25 | 70.75
[9 empty] | Total team hours over project | [5 empty] | 336.25