## Cover Page
<Product Name>
Prepared By:
Team X
<Team Member>: <Student Id>
<Team Member>: <Student Id>
<Team Member>: <Student Id>

## Product Backlog
Product Backlog
Story ID | Story Title | Card | Story Points/Size | Sprint | Status | Conversation | Confirmation
FE-1 | Main Page Buttons | As a presenter, I would like to be able to understand the functionality of each button so that I use the app without any difficulty (Story) | 1 | Sprint 1 | In Progress | There will be 5 buttons on the main page. The first one will allow the user to check the what is in front of the door, the second will be used to open a door, the third will be used to to show the user who has access to the door. The fourth used to see who last used the door and finally the last button shows the application credits | •The first button allows the user to access the camera to see what is at the door •Second butto opens the door •Thord button shows a list of user •Fourth button show who last used the door •Credits button, when pressed, brings to the activity containing the collaborators information
FE-2 | Credits Button | As a presenter, I would like to have the ability to select the credits button on the main page so that I see who collaborated on the application. (Story) | 1 | Sprint 1 | In Progress | The credit button will lead the presenter to another activity containing the information regarding the collaborators of the application | •Credits button, when pressed, brings to the activity containing the collaborators information
BE-1 | Profile | As a presenter, I want to be able to create a profile so that I can add a user as an admin(story) | 3 | Sprint 1 | In Progress | The presenter should be able to create a profile. | •Create a profile
GEN-1 | Login Page | As a presenter, I want to be able to login so that I can check who has access to the door(Story) | 3 | Sprint 1 | In Progress | The presenter should be able to create a profile if they don't have one and be able to login once they have one. | •Create an account and login
FE-3 | List of Users | As a presenter, I want the ability to view all the people who have access to the controls of application by clicking Admin (Story) | 3 | Sprint 1 | In Progress | Once the button is pressed, the user is sent to a screen showing authorized users. | •Display a list of all authorized users
GEN-2 | Display History | As a presenter, I want to check the history of the usage of the door. (Story) | 5 | Sprint 1 | In Progress | The application monitors and registers those who have unlocked the door, it display the pictures took once the user clicks the History button | •Display the list of user who used the door when History is clicked
BE-2 | Connect Sensor to Application | As a presenter, I want the motion sensor detect if anyone is at the door and send a notification delivered in history activity (Epic) | 3 | Sprint 1 | In Progress | The motion sensor notifies me when someone is at the door by detecting something with the motion sensor. | •Sensor is connected •Sensor is detecting movement and sending a notification to the application
BE-3 | Setup Database | As a user, I want my admin profile, history, and pictures to be saved on database so that I can easily access them anywhere | 13 | Sprint 1 | In Progress | The user's profile should be saved in a database, using Firebase. | •Able to add a profile to the database •Able to get the profile from the database
GEN-3 | Board Connected | As a presenter, I want to know when the board is not connected to the app so that I get to pair it with my phone (Story) | 8 | Future | Not in sprint | The presenter wants to always know if the board is connected to the phone. If it is not connected, the application will bring the presenter to another activity that will allow him/her to connect to the board. | •Check if the board is connected to the phone •If the sensor is not connected, bring the user to the connection activity
BE-4 | Connect Camera to Application | As a presenter, I want to be able to see who is at the door. (Story) | 5 | Future | Not in sprint | The camera should capture the view in front of the door if the motion sensor detects movement. | •Camera is connected •Camera takes a picture if sensor detects movement
GEN-4 | Check Door button | As a presenter, I want the ability to see who is at the door when the motion sensor is activated and notifies me using the first button. (Story) | 3 | Future | Not in sprint | The Check Door button will allow the user to access a camera and see who is at the door | •Be able to view through a camera after pressing the button
BE-4 | Unlock Door | As a presenter, I want the ability unlock the door electronically (Story) | 5 | Future | Not in sprint | The presenter will be able unlock the door and open it. | •Clicking button unlocks the door
BE-5 | Default State Locked | As a presenter, I want the make sure the door is always locked whenever I choose to not open it (Story) | 2 | Future | Not in sprint | The presenter is sure that the door is always locked unless opened by them. | •The door is always locked •The door is locked after the door is closed
GEN-5 | Open Door Button | As a presenter, I want the ability to select the Open Door button to access the door without being physically there (Epic) | 3 | Future | Not in sprint | The button allows the user to open the door without his or her presence. | •Clicking the button, opens the door
EX-1 | Gesture | A a user I want to be able to open the door using a gesture sensor using bluetooth and within a close range | 13 | Future | Not in sprint | The gesture sensor opens the door for the user when used | •The door opens with gestures
EX -2 | Face Recognition | As a admin, I want the app to scan the picture of me it took at the door so that it verifies that I am an admin and unlock the door automatically for me | 21 | Future | Not in sprint | The camera takes picture of the person at the door and scans if it is an admin | •The pictures taken are scanned •The software distinguishes an admin from others •The only opens for admin after verification
EX-3 | Accessing history requires password | As an admin I want the app to only let admin users access history page by requesting for password to open the door | 5 | Future | Not in sprint | The app only access users who have admin priviledges to view history | •Password is requested when the history button is pressed •The history page is open once ocrect password is inputted
EX-4 | Monitor who opens the door for who | As an admin I want the the history page to also record the user's device that open the door so that I can monitor which admin opens the door | 3 | Future | Not in sprint | The app shows which admin opened the door | •The history page shows the admin who opened the door along with the user that was at the door

## Sprint 1
Sprint 1 Backlog
Sprint 1 Goal(s): Finish the App skeleton,Create database server, Coding and Testing of sensor for arduino
Total ideal Hours: |  | 91
Story ID | Task ID | Task Title | Task Description | Ideal Hours |  | Status | Comments
FE-1 | FE-1 | Main Page Button | There will be 5 buttons on the main page. The first one will allow the user to check the what is in front of the door, the second will be used to open a door, the third will be used to to show the user who has access to the door. The fourth used to see who last used the door and finally the last button shows the application credits. (See Documentation/Layout_Pictures/main_page) | 2 | hrs | Planned | Assigned to: Irfan Ahmed Priority 1
FE-2 | FE-2 | Credits Button | The credit button will lead the presenter to another activity containing the information regarding the collaborators of the application | 2 | hrs | Planned | Assigned to: Irfan Ahmed Priority 5
F3-3 | F3-3 | List of Users | Once the button is pressed, the user is sent to a screen showing authorized users. | 3 | hrs | Planned | Assigned to: Cong-Vinh Vu Priority 3
GEN-2 | GEN-2 | Display History | Displays pictures taken by the camera in History page. | 5 | hrs | Planned | Assigned to: Alec Kurkdjian Priority 3
BE-1 | BE-1 | Profile | Profile of admins should contain: username, email, password, identifier of door, and a list of admins who have access to the same door. | 3 | hrs | Planned | Assigned to: Alec Kurkdjian Priority 1
GEN-1 | GEN-1.1 | Login Page | The presenter should be able to create a profile if they don't have one and be able to login once they have one by entering an door identifier, email address, password, and username. | 5 | hrs | Planned | Assigned to: Cong-Vinh Vu Priority 2
GEN-1 | GEN-1.2 | Login Page | If the user creates a profile, check for valid name and password. | 1 | hrs | Planned | Assigned to: Cong-Vinh Vu Priority 2
BE-3 | BE-3.1 | Learn Firebase | Learn how to use Firebase. | 5 | hrs | Planned | Assigned to: Alec Kurkdjian and Cong-Vinh Vu Priority 1
BE-3 | BE-3.2 | Storing Pictures in Database | Learn how to store pictures into a database. | 5 | hrs | Planned | Assigned to: Alec Kurkdjian and Cong-Vinh Vu Priority 2
BE-3 | BE-3.3 | Setup Database | The user's profile should be saved in a database, using Firebase. | 5 | hrs | Planned | Assigned to: Alec Kurkdjian and Cong-Vinh Vu Priority 1
BE-2 | BE-2.1 | Learn Arduino for Sensor | Investigate how to use Aduino and use the I/O ports. Check the analog and digital I/O ports. | 5 | hrs | Planned | Assigned to: Shadi Makdissi and Ogo-Oluwa Jesutomi Olasubulumi
BE-2 | BE-2.2 | Motion Sensor | Learn the behaviour of the senors, inputs and outputs. | 5 | hrs | Planned | Assigned to: Shadi Makdissi , Ogo-Oluwa Jesutomi Olasubulumi and Irfan Ahmed
BE-2 | BE-2.3 | Connect Sensor to Arduino Board | The Arduino should be able to receive the data from the sensor. | 5 | hrs | Planned | Assigned to: Shadi Makdissi and Ogo-Oluwa Jesutomi Olasubulumi
BE-2 | BE-2.4 | Coding Arduino Sensor | Coding Arduino to send and receive signals from the sensor using thresholds. | 5 | hrs | Planned | Assigned to: Shadi Makdissi and Ogo-Oluwa Jesutomi Olasubulumi
BE-2 | BE-2.5 | Coding Wifi Sensor | Coding Arduino to send signals using Wfi. | 5 | hrs | Planned | Assigned to: Shadi Makdissi and Ogo-Oluwa Jesutomi Olasubulumi
GEN-3 | GEN-3 | Board Connected | The presenter wants to always know if the board is connected to the phone. If it is not connected, the application will bring the presenter to another activity that will allow him/her to connect to the board. | 5 | hrs | Planned | Assigned to: Shadi Makdissi and Ogo-Oluwa Jesutomi Olasubulumi
BE-4 | BE-4.1 | Connect Camera to Arduino Board | The Arduino should be able to receive the data from the camera. | 5 | hrs | Planned | Assigned to: Shadi Makdissi and Ogo-Oluwa Jesutomi Olasubulumi
BE-4 | BE-4.2 | Coding Arduino Camera | Coding Arduino to send and receive signals from camera. | 5 | hrs | Planned | Assigned to: Shadi Makdissi and Ogo-Oluwa Jesutomi Olasubulumi
BE-4 | BE-4.2 | Learn Arduino | Learning how to use an arduino Board | 5 | hrs | Planned | Assigned to: Irfan Ahmed
BE - 4 | BE-4.4 | Coding lock for arduino | User shold be able to control the power going into the lock with the help of arduino and a relay | 5 | hrs | Planned | Assigned to: Irfan Ahmed
BE-4 | BE-4.5 | Coding Wifi Camera | Coding Arduino to send camera pictures using Wifi. | 5 | hrs | Planned | Assigned to: Shadi Makdissi and Ogo-Oluwa Jesutomi Olasubulumi

## Sprint 2
Sprint 2 Backlog
Sprint 1 Goal(s):
Total ideal Hours: |  | 0
Story ID | Task ID | Task Title | Task Description | Ideal Hours | Status | Comments