## Cover Page
<Product Name>
Prepared By:
Team X
<Team Member>: <Student Id>
<Team Member>: <Student Id>
<Team Member>: <Student Id>

## Product Backlog
Product Backlog
Story ID | Story Title | Card | Story Points | Sprint | Status | Conversation | Confirmation
FE-1 | Main Page Buttons | As a presenter, I would like to be able to understand the functionality of each button so that I use the app without any difficulty (Story) |  | Sprint 1 | Sprint 1 | There will be 3 buttons on the main page. The first button (Use App), when pressed, will bring the user to the page containing the list of all the powerpoints stored. For the second button (How to use app), when pressed, will give the user the instructions on how to use all the features implemented in the application. For the last button (Credits), when pressed, will display all the contributors of the application | •"Use App" button, when pressed, brings to the activity containg the list of PowerPoints •"How to use button" button, when pressed, brings the activity containing the instructions for the use of the app •"Credits" button, when pressed, brings to the activity containing the collaborators information
FE-2 | Credits Button | As a presenter, I would like to have the ability to select the credits button on the main page so that I see who collaborated on the application. (Story) |  | Sprint 1 | Sprint 1 | The credit button will lead the presenter to another activity containing the information regarding the collaborators of the application | •"Credits" button, when pressed, brings to the activity containing the collaborators information
FE-3 | How to Use Button | As a presenter, I want the ability to select the "how to use" button in main page so that I learn the different features offered by the application (Story) |  | Sprint 1 | Sprint 1 | The how to use button will lead the presenter to another activity containing the instructions on how to use the application | •"How to use button" button, when pressed, brings the activity containing the instructions for the use of the app
GEN-1 | Use App Button | As a presenter, I want the ability to select the "use app" button in main page so that I start utilizing the different features offered by the application (Epic) |  | Sprint 1 | Sprint 1 | The use app button will lead the presenter to another activity containng the list of all PowerPoints stored within the phone. | •"Use App" button, when pressed, brings to the activity containg the list of PowerPoints
GEN-2 | List of PowerPoint files | As a presenter, I want the ability to see all the PowerPoints at my disposal so that I can chose whichever PowerPoint I want to display with (Story) |  | Sprint 2 | Sprint 2 | Once the "use app" button has been pressed, the presenter will be on a new activity containing all the PowerPoints saved on the phone. | •Display a list of all PowerPoints
FE-4 | Display Selected PowerPoint | As a presenter, I want the ability to display the selected PowerPoint on a projector so that the audience views the contents (Story) |  | Sprint 2 | Sprint 2 | The presenter can choose from all the PowerPoints and select which one they would like to present. The one that’s chosen will be displayed onto the screen of the phone, which will then be displayed on the PC monitor | •Display the selected presentation on the phone
BE-1 | Connect Sensor to Application | As a presenter, I want the sensor to be connected to the application so I can use my motion to control the flow of the slides (Story) |  | Sprint 2 | Sprint 2 | The motion sensor should connect to the phone using Bluetooth and see if the application can detect any movement. | •Sensor is connected •Sensor is detecting movement and sending the data to the application
GEN-3 | Checking if Bluetooth is Connected | As a presenter, I want to know when the sensor is not connected to the app so that I get to pair it with my phone (Story) |  | Sprint 2 | Sprint 2 | The presenter wants to always know if the motion sensor is connected to the phone. If it is not connected, the application will bring the presenter to another activity that will allow him/her to connect to the sensor via bluetooth | •Check if the sensor is connected to the phone •If the sensor is not connected, bring the user to the connection activity
BE-2 | Move Through the Slides Using Motion | As a presenter, I want the ability to use motion to move through the slides so that I control the flow of the PowerPoint (Story) |  | Sprint 2 | Sprint 2 | The presenter will be able to use his/her movement to go through the slides of the PowerPoint whether it is to go from 1 slide to another or even to put in full screen | • Movements affect the behavior of the presentation • Specific movements make the presentation go to the next slide
BE-3 | Add New Motions to the Movement List | As a presenter, I want the ability to add new movements so that I can manipulate the flow of the slides in different ways (Story) |  | Sprint 1 | Sprint 1 | The presenter can add new movements to personalize the way they present their PowerPoint slides | •The application registers the new movements and behaves correctly according to the movement

## Sprint 1
Sprint 1 Backlog
Sprint 1 Goal(s): <Describe what you would like to achieve at the end of sprint 1>
Story ID | Task ID | Task Title | Task Description | Ideal Hours | Status | Comments
BK-1 | BK-1.1 | File/Folder Selection UI | Create a UI so user can select the files and folders that can be selectively backed up. Provide ability to select complete folder or individual files in the folder | 5 hrs | Planned
BK-1 | BK-1.2 | Backup task | Backup only files that re selected by the user. | 4 hrs | Planned
BK-2 | BK-2.1 |  | <Epic BK-2, Task 1 description> | <= 5 hrs | Planned
| BK-2.2 |  | <Epic BK-2, Task 2 description> | <= 5 hrs | Planned
| BK-2.3 |  | <Epic BK-2, Task 3 description> | <= 5 hrs | Planned