## Sheet1
[6 empty] | Team Members | [9 empty] | Instructions: Fill in only green portions. For the activities table put number 1 in the square under each name if that individual participated in that activity. The number of hours for each individual will be calculated automatically. Readjust cell size to be sure all text is visible as needed.
[6 empty] | First Name | Last Name | Nickname (max 6 characters)
[6 empty] | Irfan | Ahmed | A.I
[6 empty] | Alec | Kurkdjian | Alec
[6 empty] | Cong-Vinh | Vu | CV
[6 empty] | Shadi | Makdissi | Shadi
[6 empty] | Ogo Oluwa | Jesutomi olasubulumi | Tomi
Add more rows as necessary
Activities Table
Date | Who |  |  |  |  | Type of Activty | Number of hourse spent | Purpose | Output | Hours spent
| A.I | Alec | CV | Shadi | Tomi |  |  |  |  | A.I | Alec | CV | Shadi | Tomi
Milestone 1
2019-09-05 | 1 | 1 | 1 | 1 | 1 | Meeting | 1 | Discuss about how we will manage our code and where it will be available for all member of the teams | We decided to use GitHub to store our documentation and code for the project | 1 | 1 | 1 | 1 | 1
2019-09-09 | 2 | 2 | 2 | 0 | 2 | meeting | 2 | Brainstorm ideas and come up with 6 opportunity statement | Came up with 6 ideas and opportunity statements | 2 | 2 | 2 | 0 | 2
2019-09-14 | 2 | 0 | 2 | 2 | 2 | Voice Call meetin | 2 | Create a WOT analysis of our 6 opportunity statement | Finished ranking our opportunity statement through a WOT analysis | 2 | 0 | 2 | 2 | 2
2019-09-19 | 1 | 1 | 1 | 1 | 1 | Meeting | 1 | Set Mission Statement | Finished writing down our mission statement for the chosen opportunity statement | 1 | 1 | 1 | 1 | 1
2019-09-21 | 1 | 1 | 1 | 1 | 1 | Voice Call meeting | 1 | Finalise report for Milestone 1 | We finished setting up our milestone 1 report in a word document | 1 | 1 | 1 | 1 | 1
[9 empty] | Total hours | 7 | 5 | 7 | 5 | 7
[9 empty] | Total team hours | [5 empty] | 31
Milestone 2
2019-10-01 | 1 | 1 | 1 | 1 | 1 | Voice Call meeting | 1 | Divide Milestone 2 task | Everyone has been assigned a specefic task related to milestone 2 | 1 | 1 | 1 | 1 | 1
2019-10-04 | 1 | 1 | 1 | 1 | 1 | Face to face meeting with stakeholder 1 | 1 | Interview with stakeholder 1 | Gathered information on stakeholder 1 and his point of view on our product | 1 | 1 | 1 | 1 | 1
2019-10-05 | 1 | 1 | 1 | 1 | 1 | Face to face meeting with stakeholder 2 | 1 | Interview with stakeholder 2 | Gathered information on stakeholder 1 and his point of view on our product | 1 | 1 | 1 | 1 | 1
2019-10-07 | 1 | 1 | 1 | 1 | 1 | Meeting | 1 | Finalise report for Milestone 2 | We finished setting up our milestone 2 report in a word document | 1 | 1 | 1 | 1 | 1
[9 empty] | Total hours | 4 | 4 | 4 | 4 | 4
[9 empty] | Total team hours | [5 empty] | 20
Sprint 1
[10 empty] | 0 | 0 | 0 | 0 | 0
[9 empty] | Total hours | 0 | 0 | 0 | 0 | 0
[9 empty] | Total team hours | [5 empty] | 0
Sprint 2
[10 empty] | 0 | 0 | 0 | 0 | 0
[9 empty] | Total hours | 0 | 0 | 0 | 0 | 0
[9 empty] | Total Team hours | [5 empty] | 0
Sprint 3
[10 empty] | 0 | 0 | 0 | 0 | 0
[9 empty] | Total hours | 0 | 0 | 0 | 0 | 0
[9 empty] | total team hours | [5 empty] | 0
[9 empty] | Total hour over project | 11 | 9 | 11 | 9 | 11
[9 empty] | Total team hours over project | [5 empty] | 51