## Cover Page
Open Sesame
Prepared By:
Team D
Shadi Makdissi: 40060588
Cong-Vinh Vu: 40061685
Alec Kurkdjiani: 40056402
Irfan Ahmed: 40056645
Ogo-Oluwa Jesutomi Olasubulumi: 40055693

## Product Backlog
Product Backlog
Story ID | Story Title | Card | Story Points/Size | Sprint | Status | Conversation | Confirmation
FE-1 | Main Page Buttons | As a presenter, I would like to be able to understand the functionality of each button so that I use the app without any difficulty (Story) | 1 | Sprint 1 | Completed | There will be 5 buttons on the main page. The first one will allow the user to check the what is in front of the door, the second will be used to open a door, the third will be used to to show the user who has access to the door. The fourth used to see who last used the door and finally the last button shows the application credits | • The first button allows the user to access the camera to see what is at the door • Second butto opens the door • Thord button shows a list of user • Fourth button show who last used the door • Credits button, when pressed, brings to the activity containing the collaborators information
FE-2 | Credits Button | As a presenter, I would like to have the ability to select the credits button on the main page so that I see who collaborated on the application. (Story) | 1 | Sprint 1 | Completed | The credit button will lead the presenter to another activity containing the information regarding the collaborators of the application | • Credits button, when pressed, brings to the activity containing the collaborators information
BE-1 | Profile | As a user, I want to be able to create a profile so that I can myself as an administrator. (Story) | 3 | Sprint 1 | Completed | The presenter should be able to create a profile. | • Create a profile
GEN-1 | Login Page | As a presenter, I want to be able to login so that I can have access to the application's functionnalities. (Story) | 3 | Sprint 1 | Completed | The presenter should be able to create a profile if they don't have one and be able to login once they have one. | • Create an account and login
GEN-2 | Display History | As a presenter, I want to check the history of the usage of the door to see who had previously showed up at my door. (Story) | 5 | Sprint 1 | Completed | The application monitors and registers those who have unlocked the door, it display the pictures took once the user clicks the History button | • Display a list of pictures when History is clicked
BE-3 | Setup Database | As a user, I want my admin profile, history, and pictures to be saved on database so that I can easily access them anywhere | 3 | Sprint 1 | Completed | The user's profile should be saved in a database, using Firebase. | • Able to add a profile to the database • Able to get the profile from the database
GEN-6 | Embedded Door | As an user, I want to have the system already integrated to a door so that it maximizes the responsiveness of the product and minimizes space comsumption. (Epic) | 3 | Sprint 2 | Sprint 2 | The should have a door which can use the functionnalities of our application, by creating an embedded system on a door. | • Have a door which works with the application
GEN-7 | Lock for Door | As an user, I want to have a lock on my door which is responsive to the applcaition to allow me to prevent intrusion. (Story) | 3 | Sprint 2 | Sprint 2 | The lock should be embedded on the door and be rsponsive to commnads coming from the application. | • Lock is on the door • Lock respond to application
GEN-8 | Camera Holder | As an user, I want camera to be fixed near the door to take pictures of anything in front of it. (Story) | 3 | Sprint 2 | Sprint 2 | The motion sensor notifies me when someone is at the door by detecting something with the motion sensor. | • Sensor is connected • Sensor is detecting movement and sending a notification to the application
GEN-9 | Arduino Holder | As an user, I want circuits to be embedded on the door for minimal space usage. (Story) | 3 | Sprint 2 | Sprint 2 | The motion sensor notifies me when someone is at the door by detecting something with the motion sensor. | • Sensor is connected • Sensor is detecting movement and sending a notification to the application
BE-2 | Connect Sensor to Application | As a presenter, I want the motion sensor detect if anyone is at the door and send a notification delivered in history activity (Epic) | 3 | Sprint 2 | Sprint 2 | The motion sensor notifies me when someone is at the door by detecting something with the motion sensor. | • Sensor is connected • Sensor is detecting movement and sending a notification to the application
GEN-3 | Wifi Connected | As a presenter, I want to know when the application is not connected to Wifi so that I can connect it manually. (Story) | 8 | Sprint 2 | Sprint 2 | The presenter wants to always know if the board is connected to the phone. If it is not connected, the application will bring the presenter to another activity that will allow him/her to connect to the board. | • Check if the board is connected to the phone • If the sensor is not connected, bring the user to the connection activity
BE-4 | Connect Camera to Application | As a presenter, I want to be able to see who is at the door to allow or deny access. (Story) | 5 | Sprint 2 | Sprint 2 | The camera should capture the view in front of the door if the motion sensor detects movement. | • Camera is connected • Camera takes a picture if sensor detects movement
BE-5 | Unlock Door | As a presenter, I want the ability unlock the door electronically (Story) | 5 | Sprint 2 | Sprint 2 | The presenter will be able unlock the door and open it. | • Clicking button unlocks the door
FE-3 | List of Users | As a presenter, I want the ability to view all the people who have access to the controls of application by clicking Administrators to see who has the same privilleges as me. (Story) | 5 | Sprint 2 | Sprint 2 | Once the button is pressed, the user is sent to a screen showing authorized users. | • Display a list of all authorized users
BE-6 | Reset Password | As an user, I want to be able to reset my password through my email to grant me access to the apllication in case of forgetting my password. (Story) | 5 | Sprint 2 | Sprint 2 | The user gets a email, sent by the application, to to reset his password. The new password is then updated on to the database. | • Get email to reset password • Password is stored in the database
FE-4 | Embellish Application | As an user, I want to have a friendly graphical user interface to understand easily what the application does. (Story) | 1 | Sprint 2 | Sprint 2 | The user should have in front of him an easy to understand application with decorative backgrounds to appeal to the larger public . | • Confirmation from the stakeholders
GEN-9 | Delete Users | As an user, I want to be able remove others from the list of users to deny access to unwanted users. (Story) | 2 | Sprint 2 | Sprint 2 | The user should be able to add additionnal doors to the appliaction, in order to access them by deleting other in Administrators page. | • The door is always locked • The door is locked after the door is closed
GEN-10 | Modify Profile | As an user, I want be able to modify values in my profile to represent my present reality. (Story) | 2 | Sprint 2 | Sprint 2 | The user should be directed to a profile page to change her username, email, or password. | • Be able to peek and unlock multiple doors
BE-5 | Add Doors to Profile | As an user, I want to be able to control multiple doors through the application to minimize the amount of time I need to log in and log out. (Story) | 2 | Future | Not in sprint | The application should allow users to prevent others from unlocking a door. | • Deleting a user removes them from the database • Requires them to Sign Up again
BE-7 | Default State Locked | As a presenter, I want the make sure the door is always locked whenever I choose to not open it to ensure security. (Story) | 2 | Future | Not in sprint | The presenter is sure that the door is always locked unless opened by them. | • Be able to peek and unlock multiple doors
GEN-5 | Open Door Button | As a presenter, I want the ability to select the Open Door button to access the door without being physically there to save time and energy. (Epic) | 3 | Future | Not in sprint | The button allows the user to open the door without his or her presence. | • Clicking the button, opens the door
EX-1 | Gesture | As an user, I want to be able to open the door using a gesture sensor using bluetooth and within a close range to minimize the range and mouvements needed to open a door. (Epic) | 13 | Future | Not in sprint | The gesture sensor opens the door for the user when used | • The door opens with gestures
EX -2 | Facial Recognition | As an administrator, I want the app to scan the picture of me it took at the door so that it verifies that I am an admin and unlock the door automatically for me. (Epic) | 21 | Future | Not in sprint | The camera takes picture of the person at the door and scans if it is an admin | • The pictures taken are scanned • The software distinguishes an admin from others • The only opens for admin after verification
EX-4 | Monitor | As an administrator, I want the the history page to also record the user's device that open the door so that I can monitor which administrators opens the door (Epic) | 3 | Future | Not in sprint | The app shows which administrator has opened the door. (Epic) | • The history page shows the admin who opened the door along with the user that was at the door
GEN-4 | Peek Door button | As a presenter, I want the ability to see who is at the door when the motion sensor is activated and notifies me using the first button to allow me to permit or deny entrance. (Story) | 3 | Sprint 2 | Sprint 2 | The Peek Door button will allow the user to access a camera and see who is at the door | • Be able to view through a camera after pressing the button

## Sprint 1
Sprint 1 Backlog
Sprint 1 Goal(s): Start the Applicationès Skeleton, Create Database, Coding and Testing of Sensors for Arduino
Total ideal Hours: |  | 78
Story ID | Task ID | Task Title | Task Description | Ideal Hours |  | Status | Comments
FE-1 | FE-1 | Main Page Button | There will be 5 buttons on the main page. The first one will allow the user to check the what is in front of the door, the second will be used to open a door, the third will be used to to show the user who has access to the door. The fourth used to see who last used the door and finally the last button shows the application credits. (See Documentation/Layout_Pictures/main_page) | 2 | hrs | Completed | Assigned to: Irfan Ahmed Priority 1 Done: Main Page contains all 5 buttons
FE-2 | FE-2 | Credits Button | The credit button will lead the presenter to another activity containing the information regarding the collaborators of the application | 2 | hrs | Completed | Assigned to: Irfan Ahmed Priority 5 Done: Credits contain infromation on project engineer and devlopers
GEN-2 | GEN-2.1 | Display History | Displays pictures taken by the camera in History page. | 5 | hrs | Completed | Assigned to: Alec Kurkdjian Priority 3 Done: After clicking History, gets pictures uploaded to database and puts them in a list
BE-1 | BE-1 | Profile | Profile of admins should contain: username, email, password, identifier of door, and a list of admins who have access to the same door. | 3 | hrs | Completed | Assigned to: Alec Kurkdjian Priority 1 Done: Completed a profile class which encompass everything needed fro an user
GEN-1 | GEN-1.1 | Login Page | The presenter should be able to create a profile if they don't have one and be able to login once they have one by entering an door identifier, email address, password, and username. | 5 | hrs | Completed | Assigned to: Cong-Vinh Vu Priority 2 Done: Allow the user to sign up and log in
GEN-1 | GEN-1.2 | Login Page | If the user creates a profile, check for valid name and password. | 1 | hrs | Completed | Assigned to: Cong-Vinh Vu Priority 2 Done: Does not allow invalid inputs in username, email, password and door identifier fields
BE-3 | BE-3.1 | Learn Firebase | Learn how to use Firebase. | 5 | hrs | Completed | Assigned to: Alec Kurkdjian & Cong-Vinh Vu Priority 1 Done: be able to create a dtabase class
BE-3 | BE-3.2 | Storing Pictures in Database | Learn how to store pictures into a database. | 5 | hrs | Completed | Assigned to: Alec Kurkdjian & Cong-Vinh Vu Priority 2 Done: Able to store pictures inside the database
BE-3 | BE-3.3 | Setup Database | The user's profile should be saved in a database, using Firebase. | 5 | hrs | Completed | Assigned to: Alec Kurkdjian & Cong-Vinh Vu Priority 1 Done: Create a databaseHelper class and be able to uplaod and retrieve information from it
BE-2 | BE-2.1 | Learn Arduino for Sensor | Investigate how to use Aduino and use the I/O ports. Check the analog and digital I/O ports. | 5 | hrs | Completed | Assigned to: Shadi Makdissi & Ogo-Oluwa Jesutomi Olasubulumi Done: Get data from the sensors
BE-2 | BE-2.2 | Motion Sensor | Learn the behaviour of the senors, inputs and outputs. | 5 | hrs | Completed | Assigned to: Shadi Makdissi , Ogo-Oluwa Jesutomi Olasubulumi ,& Irfan Ahmed Done: Able to test and adjust the range of the sensor
BE-2 | BE-2.3 | Connect Sensor to Arduino Board | The Arduino should be able to receive the data from the sensor. | 5 | hrs | Completed | Assigned to: Shadi Makdissi & Ogo-Oluwa Jesutomi Olasubulumi Done: Able to use the serial monitor
BE-2 | BE-2.4 | Coding Arduino Sensor | Coding Arduino to send and receive signals from the sensor using thresholds. | 5 | hrs | Completed | Assigned to: Shadi Makdissi & Ogo-Oluwa Jesutomi Olasubulumi Done: Get signals from the sensor
BE-2 | BE-2.5 | Coding Wifi Sensor | Coding Arduino to send signals using Wfi. | 5 | hrs | Completed | Assigned to: Shadi Makdissi & Ogo-Oluwa Jesutomi Olasubulumi Done: Control the LEDs with Wifi server
BE-4 | BE-4.1 | Connect Camera to Arduino Board | The Arduino should be able to receive the data from the camera. | 5 | hrs | Completed | Assigned to: Shadi Makdissi & Ogo-Oluwa Jesutomi Olasubulumi Done: Receive the image from the camera
BE-4 | BE-4.2 | Coding Arduino Camera | Coding Arduino to send and receive signals from camera. | 5 | hrs | Completed | Assigned to: Shadi Makdissi & Ogo-Oluwa Jesutomi Olasubulumi Done: Receive electrical signals from the camera
BE-4 | BE-4.3 | Learn Arduino | Learning how to use an Arduino Board | 5 | hrs | Completed | Assigned to: Irfan Ahmed Done: Read documentation on Arduino board
BE - 4 | BE-4.4 | Coding Lock | User shold be able to control the power going into the lock with the help of arduino and a relay | 5 | hrs | Completed | Assigned to: Irfan Ahmed Done: Able to control the lock's mechanism

## Sprint 2
Sprint 2 Backlog
Sprint 2 Goal(s): Communication with Database and Finish Back-End Heavy Tasks
Total ideal Hours: |  | 98
Story ID | Task ID | Task Title | Task Description | Ideal Hours |  | Status | Comments
BE-2 & BE-4 | BE-2.4.1 | Multiple Sensors | All sensors should be able to work simultaneously when connected together. | 5 | hrs | Planned | Assigned to: Shadi Makdissi & Ogo-Oluwa Jesutomi Olasubulumi Priority 2
BE-2 & BE-4 | BE-2.4.1 | Connect Arduino Wifi | Arduino and wifi module should be connected with good communication between both devices. | 5 | hrs | Planned | Assigned to: Shadi Makdissi & Ogo-Oluwa Jesutomi Olasubulumi Priority 1
BE-2 & BE-4 | BE-2.4.1 | Connect Arduino Database | Arduino should be able to connect to the firebase server. | 5 | hrs | Planned | Assigned to: Shadi Makdissi & Ogo-Oluwa Jesutomi Olasubulumi Priority 2
BE-4 | BE-4.5 | Coding Wifi Camera | Coding Arduino to send camera pictures to Wifi server. | 5 | hrs | Planned | Assigned to: Shadi Makdissi & Ogo-Oluwa Jesutomi Olasubulumi Priority 3
BE-4 | BE-4.6 | Camera Pictures to Database | Arduino should be able to send pictures to Firebase. | 5 | hrs | Planned | Assigned to: Shadi Makdissi & Ogo-Oluwa Jesutomi Olasubulumi Priority 3
GEN-7 | GEN-7.1 | Add Lock | The lock system should be installed on the door. | 2 | hrs | Planned | Assigned to: Irfan Ahmed Priority 1
GEN-7 | GEN-7.2 | Instructions from Database | Arduino should be able to take instructions from Firebase and implement it. | 5 | hrs | Planned | Assigned to: Shadi Makdissi & Ogo-Oluwa Jesutomi Olasubulumi Priority 2
GEN-7 | GEN-7.3 | Instructions to Database | The application should be able to send instructions to the database. | 3 | hrs | Planned | Assigned to: Irfan Ahmed & Alec Kurkdjian Priority 2
FE-4 | FE-4 | Embellish Application | The design of the app should be updated to the desired design. | 3 | hrs | Planned | Assigned to: Irfan Ahmed Priority 3
GEN-6.1 | GEN-6.1 | Building Prototype Door | The prototype door to be used for testing should be built. | 5 | hrs | Planned | Assigned to: Irfan Ahmed Priority 4
GEN-8 | GEN-8 | Camera Holder | A 3D-printed model to be made to hold the camera. | 2 | hrs | Planned | Assigned to: Irfan Ahmed Priority 5
GEN-9 | GEN-9 | Arduino Holder | A 3D-printed model to be made to hold the arduino by the door. | 4 | hrs | Planned | Assigned to: Shadi Makdissi & Ogo-Oluwa Jesutomi Olasubulumi Priority 5
WR | WR | Sprint 3 Preparations | Documents needed for sprint 3 should be done. | 3 | hrs | Planned
TEST | TEST | Testing | Testing and validation of all task to be done in Sprint 2. | 4 | hrs | Planned | Assigned to: Irfan Ahmed Priority 5
F3-3 | F3-3 | List of Users | Once the button is pressed, the user is sent to a screen showing authorized users. | 5 | hrs | Planned | Assigned to: Cong-Vinh Vu Priority 1
GEN-3 | GEN-3 | Wifi Connected | The user should be notified if they are not connected to the internet. | 5 | hrs | Planned | Assigned to: Shadi Makdissi & Ogo-Oluwa Jesutomi Olasubulumi Priority 3
BE-6 | BE-6.1 | Reset Password | The applcaition should send an email to the user after clicking I Forgot My Password, to allow the user to reset their own password. | 5 | hrs | Planned | Assigned to: Cong-Vinh Vu & Alec Kurkdjian Priority 3
BE-6 | BE-6.2 | Reset Password | The new password entered by the user should be saved into the database, replacing the old one. | 5 | hrs | Planned | Assigned to: Cong-Vinh Vu & Alec Kurkdjian Priority 3
GEN-1 | GEN-1.3 | Login Page | Refactor the Login and Sign Up functionnalities. | 2 | hrs | Planned | Assigned to: Cong-Vinh Vu Priority 1
GEN-1 | GEN-1.4 | Login Page | The application should not allow two duplicate users inside the database. | 3 | hrs | Planned | Assigned to: Cong-Vinh Vu Priority 1
GEN-1 | GEN-1.5 | Login Page | The application should not allow the usage of same emails and usernames. | 3 | hrs | Planned | Assigned to: Cong-Vinh Vu Priority 1
GEN-2 | GEN-2.2 | Display History | Refactor the Display History functionnalities. | 3 | hrs | Planned | Assigned to: Alec Kurkdjian Priority 1
GEN-2 | GEN-2.3 | Display History | Use Cloud Firestore to store data instead of Firebase's Real Time Database. | 3 | hrs | Planned | Assigned to: Alec Kurkdjian Priority 1
GEN-9 | GEN-9 | Delete Users | Delete users by clicking a delete button in the Administrators page. | 4 | hrs | Planned | Assigned to: Cong-Vinh Vu Priority 2
GEN-10 | GEN-10 | Modify Profile | Create a profile page and allow user to modify their credentials. | 4 | hrs | Planned | Assigned to: Alec Kurkdjian & Irfan Ahmed Priority 2